## Table 1
PLEASE NOTE THAT THIS IS AN EXAMPLE ONLY AND ILLUSTRATES THE TYPES OF TASK THAT SHOULD BE INCLUDED IN A WORK PLAN - YOUR WORK PLAN SHOULD BE BASED UPON YOUR PLANNED ACTIVITY AND TIMESCALE
Work Plan - 2020 Rally Safety Training Programme
[5 empty] | MARCH |  |  |  |  | APRIL |  |  |  | MAY |  |  |  |  | JUNE |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  | DECEMBER
Training Task Description | Training Task Leader | Task Start Date | Task End Date | Duration of Task | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK5 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4 | WK1 | WK2 | WK3 | WK4
Finalise project strategy with RTP | Project Manager | 2020-03-04 | 2020-03-08 | 1 week | bar: MARCH WK2
Finalise budget with RTP | Project Manager | 2020-03-11 | 2020-03-15 | 1 week | bar: MARCH WK3
Assess training needs for officials at all levels | Project Coordinator & RTP Trainers | 2020-03-18 | 2020-03-29 | 2 weeks | bar: MARCH WK4 to MARCH WK5
Develop curriculum with RTP | Project Coordinator & RTP Trainers | 2020-04-01 | 2020-04-26 | 4 weeks | bar: APRIL WK1 to APRIL WK4
Finalise training schedule and launch | Project Coordinator & RTP trainers | 2020-05-13 | 2020-05-17 | 1 week | bar: MAY WK3
Plan logistics for training programme | Project Coordinator | 2020-06-10 | 2020-06-14 | 1 week | bar: JUNE WK2
Book venue and finalise RTP travel dates | Project Coordinator | 2020-06-24 | 2020-06-28 | 1 week | bar: JUNE WK4
Invite participants | Project Coordinator | 2020-07-01 | 2020-07-05 | 1 week | bar: JULY WK1
Organise travel and accommodation for participants | Project Coordinator | 2020-07-25 | 2020-07-31 | 1 week | bar: JULY WK4
Module 1 + assessment: Event safety management/planning | RTP trainers | 2020-10-05 | 2020-10-06 | 2 days | bar: OCTOBER WK1
Module 2 + assessment: Driver, spectator and official safety | RTP trainers | 2020-10-12 | 2020-10-13 | 2 days | bar: OCTOBER WK2
Module 3 + assessment: CoC & Stage Commander training | RTP trainer | 2020-10-19 | 2020-10-20 | 2 days | bar: OCTOBER WK3
Module 4 + assessments: Emergency response training | RTP trainers | 2020-10-26 | 2020-10-27 | 2 days | bar: OCTOBER WK4
Collate and analyse participant results and feedback | Project Coordinator & RTP trainers | 2020-11-25 | 2020-11-26 | 2 days | bar: NOVEMBER WK4
Write and present RTP Assessment Report | RTP Trainers | 2020-12-02 | 2020-12-06 | 1 week | bar: DECEMBER WK1
Meet to discuss future developments | Project Mgr, Coordinator and RTP trainers | 2020-12-09 | 2020-12-09 | 1 day | bar: DECEMBER WK2